## Sheet1
| Group Topic: | Autonomous Response Drone | [6 empty] | Advisor Signature | Date
| Advisor: | Kaikai Liu | [7 empty] | 2017-12-06
| Group Members: | Ali Baqar
Anahit Sarao
Maxwell Cheshier
Brian Josefowicz
|  | Group only Meetings |  |  | Advisor Meetings |  | Meeting Results
Week # | Week begins with: | Date | Time | Location | Date | Time | Attendees (First names of group members only plus the professor's name if in attendance) | Length of meeting | Key points covered
1 | 2017-08-21 | 2017-08-27 | 9:00AM | ENGR BLDG | N/A |  | All group members were in attendance | 6 hours | Firmware flash, autopilot software, drone testing
2 | 2017-08-28 | 2017-09-03 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 2 hours | Reveiewed option for gaining autonomous flight. Need to send GPS coordinates to drone | Submit this chart
3 | 2017-09-04 | 2017-09-10 | 9:00AM | ENGR BLDG | 2017-09-06 | 4:00PM | Brian and Professor Kaikai | 3 hours
4 | 2017-09-11 | 2017-09-17 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 2 hours | Created bill of materials. Researched GPS options. Created/finalized drone hardware schematics
5 | 2017-09-18 | 2017-09-24 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 4 hours | Set up GCS software and implemented PX4 testing. Spec'd out GPS module . Designed implementation for RPi to Crazyflie
6 | 2017-09-25 | 2017-10-01 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 3 hours
7 | 2017-10-02 | 2017-10-08 | 9:00AM | ENGR BLDG | 2017-10-04 | 4:00PM | Brian, Ali, Professor Kaikai | 5 hours | Met at ABET expo; showcased the project for the Accredation Board and discussed with other teams some ideas and improvements. Advisor was also present
8 | 2017-10-09 | 2017-10-15 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 2.5 hours | Revised chapters 1-3 of workbook. Finalized chapters 4 and 5 of workbook. Prepared drones for hardware integration
9 | 2017-10-16 | 2017-10-22 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 2 hours |  | Submit this chart
10 | 2017-10-23 | 2017-10-24 | 9:00AM | ENGR BLDG | 2017-10-24 | 16:30 | Max, Brian, Ali, Anahit | 1 hour | Met with Rajarth to discuss GPS implementation and part to be ordered
11 | 2017-10-30 | 2017-11-05 | 9:00AM | ENGR BLDG | N/A
12 | 2017-11-06 | 2017-11-12 | 9:00AM | ENGR BLDG | 2017-11-06 | 16:00 | Ali | 1 hour | Picked up GPS module, talked about getting help from Rajarth
13 | 2017-11-13 | 2017-11-19 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 4 hours | Worked on implementing the GPS module. Worked with flashing the controller with PX4 firmware | Draft Report due this week
14 | 2017-11-20 | 2017-11-26 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 2 hours | Worked on integrating crazyFlie controller with full stack (GPS and RPi) with the Xiro drone in the hardware mounting chassis
15 | 2017-11-27 | 2017-12-03 | 9:00AM | ENGR BLDG | N/A |  | Max, Brian, Ali, Anahit | 3 hours | Tested the drone | Submit this chart
16 | 2017-12-04 | 2017-12-10 | 9:00AM | ENGR BLDG | 2017-12-04 | 4:00PM | Ali | 30 mins | edits to be made to report | Final Project signoff due this week
Fill in shaded parts above for 1st submission
Update any changes in green areas that and fill out blue areas for second submission
Update any changes in green areas and fillout yellow areas for third submission